## USDA_Funding_Analysis
FUNDING ANALYSIS
Project Name: | Tubac Fire Station No. 1 |  | Pay Application #: | 5
Date: |  |  | Period To:
EXPENDITURES | Contractor | Budgeted | Obligated | Expended | Bal to Finish | Projected | Total | Curr Request | Notes
Construction – GMP | D.L. Norton General Contracting, Inc. | 7494240 | 7494240 | 673649.87 | 6820590.13 |  | 7494240 | 221948.64 | Pay app#4- sitework,retanining walls, spetic system, water service
FUNDING SOURCES
Source | Total Budget | Prior Draw | This Draw | Balance Remaining | Notes
USDA Grant | 2000000 | 673649.87 | 221948.64 | 1104401.49 | Drawn first CDS grant.
Bond Funds | 4200000 | 0 | 0 | 4200000 | Used after USDA funds are exhausted.
Capital Reserve | 1294240 | 0 | 0 | 1294240 | Drawn last; remaining balance stays in LPG account.
Contigency Funds | 350000 |  | 3500 | 346500 | Exploratory digging for water line

## Board_Chart
Pay App # | USDA | Bonds | Capital Reserve | Total Pay App
1 | 227600.52 | 0 | 0 | 227600.52
2 | 126287.02 | 0 | 0 | 126287.02
3 | 242871.03 | 0 | 0 | 242871.03
4 | 76891.3 | 0 | 0 | 76891.3
5 | 221948.64 | 0 | 0 | 221948.64
Total | 895598.51 | 0 | 0 | 895598.51
Contingency Funds
Total | 350000
Used | 3500
Remaining | 346500

## USDA_Funding_Summary
USDA Funding Summary – Tubac Fire Station No. 1
Total Earned This Period | 230220.45
Retainage | 8271.81
Net Pay Requested | 221948.64
USDA Funds Applied This Pay App | 221948.64
USDA Funds Drawn To Date | 895598.51
USDA Grant Total | 2000000
USDA Remaining | 1104401.49
Work Completed This Period
Sitwork,septic system,building footings

## Cumulative_Summary
Cumulative Net & Retainage Summary
Pay App # | Gross This Pay App | Retainage This Pay App | Net This Pay App | Cumulative Gross | Cumulative Retainage | Cumulative Net
1 | 234473.08 | 6872.56 | 227600.52 | 234473.08 | 6872.56 | 227600.52
2 | 129569.83 | 3282.81 | 126287.02 | 364042.91 | 10155.37 | 353887.54
3 | 251277.37 | 8406.34 | 242871.03 | 615320.28 | 18561.71 | 596758.57
4 | 77527.24 | 635.94 | 76891.3 | 692847.52 | 19197.65 | 673649.87
5 | 230220.45 | 8271.81 | 221948.64 | 923067.97 | 27469.46 | 895598.51

## SOV_Master
Division | Division Name | Item No. | Description | Unit | Qty | Unit Price | Bid Cost
1 | General Requirements | 1 | Safety/First Aid/ Eyewash Stn. | ls | 1 | 850 | 850
1 | General Requirements | 2 | Temporary Fire Protections | ls | 1 | 450 | 450
1 | General Requirements | 3 | Temporary Storage Container | ls | 1 | 2500 | 2500
1 | General Requirements | 4 | Temporary Building Protection | ls | 1 | 3000 | 3000
1 | General Requirements | 5 | Temporary Fence | ls | 1 | 6500 | 6500
1 | General Requirements | 6 | Temporary Job Trailer | ls | 1 | 30000 | 30000
1 | General Requirements | 7 | Temporary Power Job Trailer | ls | 1 | 13500 | 13500
1 | General Requirements | 8 | Job Trailer Drinking Water | ls | 1 | 1250 | 1250
1 | General Requirements | 9 | Temporary Toilets & Sanitation | ls | 1 | 7500 | 7500
1 | General Requirements | 10 | Temporary Handwash Station | ls | 1 | 1500 | 1500
1 | General Requirements | 11 | Progress & Final Cleaning | ls | 1 | 10500 | 10500
1 | General Requirements | 12 | Dumpster/Trash Disposal | ls | 1 | 24000 | 24000
1 | General Requirements | 13 | Street Sweeper | ls | 1 | 5000 | 5000
1 | General Requirements | 14 | Traffic Control | ls | 1 | 5800 | 5800
1 | General Requirements | 15 | Warranty | ls | 1 | 5000 | 5000
2 | Existing Conditions | 1 | Survey & Staking | ls | 1 | 21650 | 21650
3 | Concrete | 1 | Decorative Concrete Finishes | ls | 1 | 32006.85 | 32006.85
4 | Masonry & Precast Concrete | 1 | Masonry & Precast Concrete | ls | 1 | 512000 | 512000
5 | Metals | 1 | Structural Steel & Misc. Steel | ls | 1 | 136635 | 136635
6 | Wood, Plastics, and Composites | 1 | Rough Carpentry | ls | 1 | 257800 | 257800
6 | Wood, Plastics, and Composites | 2 | Architectural Wood & Countertop | ls | 1 | 113320 | 113320
7 | Thermal & Moisture Protection | 1 | Roofing & Appendages | ls | 1 | 427764 | 427764
7 | Thermal & Moisture Protection | 2 | Joint Sealants | ls | 1 | 18665 | 18665
8 | Openings | 1 | HM Frames, Doors & Hardware | ls | 1 | 92866 | 92866
8 | Openings | 2 | Aluminum Frames, Storefronts, Windows, Glazing | ls | 1 | 66596 | 66596
8 | Openings | 3 | Overhead Sectional & Coiling Doors | ls | 1 | 78610 | 78610
8 | Openings | 4 | Unit Skylights & Tubular Solatube | ls | 1 | 22691.12 | 22691.12
9 | Finishes | 1 | Framing, Insulation, Drywall, Paint, ACT, FRP | ls | 1 | 319743 | 319743
9 | Finishes | 2 | Stucco | ls | 1 | 106849.56 | 106849.56
9 | Finishes | 3 | Tile, Athletic Flooring, Rubber Base | ls | 1 | 29548 | 29548
10 | Specialties | 1 | Exterior & Interior Building Signage | ls | 1 | 22094 | 22094
10 | Specialties | 2 | Toilet & Bath Accessories | ls | 1 | 8845 | 8845
10 | Specialties | 3 | FEC (excludes fire extinguishers) & Corner Guards | ls | 1 | 4170 | 4170
10 | Specialties | 4 | Flagpoles | ls | 1 | 11781.31 | 11781.31
12 | Furnishings | 1 | Window Coverings | ls | 1 | 4750 | 4750
21 | Fire Suppression | 1 | Fire Sprinkler Systems | ls | 1 | 39000 | 39000
22 | Plumbing (Includes Mechanical) | 1 | Plumbing & Mechanical Systems | ls | 1 | 657153 | 657153
26 | Electrical (Includes Fire Alarm) | 1 | Electrical & Fire Alarm Systems | ls | 1 | 1058127 | 1058127
31/32 | Earthwork & Exterior Improvements | 1 | Demo, Fill, Grading, Utilities, Septic System, Building & Site Concrete and Asphalt | ls | 1 | 1205959.2 | 1205959.2
31/32 | Earthwork & Exterior Improvements | 2 | Asphalt Striping & Site Signage | ls | 1 | 3962.7 | 3962.7
31/32 | Earthwork & Exterior Improvements | 3 | Termite Control | ls | 1 | 8084 | 8084
31/32 | Earthwork & Exterior Improvements | 4 | Fence, Gates, Guardrail & Handrail | ls | 1 | 111127 | 111127
31/32 | Earthwork & Exterior Improvements | 5 | Landscape & Irrigation | ls | 1 | 49633 | 49633

## Pay_Apps
Pay Application Funding Tracker - Sequential Use of Funds (USDA → Bonds → Capital Reserve)
USDA Total | 2000000 | Bonds Total | 4200000 | Capital Reserve Total | 1294240 | GMP #1 Total | 7494240
|  |  |  | USDA - This Pay App | Running Total | Bonds - This Pay App |  | Capital Reserve - This Pay App |  | USDA Remaining | Bonds Remaining | Capital Reserve Remaining | Total Project Remaining
Pay App # | Date | Pay App Amount
1 | 2025-11-24 | 227600.52 | 227600.52 | 227600.52 | 227600.52 | 0 | 0 | 0 | 0 | 1772399.48 | 4200000 | 1294240 | 7266639.48
2 | 2025-11-28 | 126287.02 | 353887.54 | 126287.02 | 353887.54 | 0 | 0 | 0 | 0 | 1646112.46 | 4200000 | 1294240 | 7140352.46
3 | 2025-12-23 | 242871.03 | 596758.57 | 242871.03 | 596758.57 | 0 | 0 | 0 | 0 | 1403241.43 | 4200000 | 1294240 | 6897481.43
4 | 2026-01-28 | 76891.3 | 673649.87 | 76891.3 | 673649.87 | 0 | 0 | 0 | 0 | 1326350.13 | 4200000 | 1294240 | 6820590.13
5 | 2026-02-25 | 221948.64 | 895598.51 | 221948.64 | 895598.51 |  | 0 | 0 | 0 | 1104401.49 | 4200000 | 1294240 | 6598641.49
|  |  | 895598.51 | 1104401.49 | 2000000 | -1104401.49 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49
|  |  | 895598.51 | 0 | 2000000 | 0 | -1104401.49 | 0 | 0 | 0 | 5304401.49 | 1294240 | 6598641.49

## PayApp5
Pay Application #5 Summary (per AIA G702)
Gross This Pay App | 230220.45 |  | Net Payment This Pay App | 221948.64
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date | Retainage To Date (Per Pay App #4) | Net This pay app
1 | General Requirements | 124267.86 | 5487.63 | 205.62 | 51022.52 | 2551.13 | 5282.01
2 | Survey & Staking | 21650 | 1575 | 59.02 | 9333.75 | 466.69 | 1515.98
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 59382 | 2225.06 | 59382 | 2969.1 | 57156.94
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 85527 | 3204.72 | 349377 | 17468.85 | 82322.28
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 | 0 | 0
28 | Termite Control | 8084 | 0 | 0 | 0 | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 | 0 | 0
36 | General Conditions | 740250 | 53672.46 | 2011.12 | 270475.96 | 0 | 51661.34
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1647.83 | 61.75 | 9879.05 | 0 | 1586.08
39 | Consturuction Fee | 438579.88 | 13464.4 | 504.52 | 54033.04 | 2701.65 | 12959.88
40 | Sales Tax | 308277.78 | 9464.13 | 0 | 37979.82 | 0 | 9464.13
| Totales | 7437427 | 230220.45 | 8271.81 | 923067.97 | 27469.46 | 221948.64

## PayApp4
Pay Application #4 Summary (per AIA G702)
Gross This Pay App | 77527.24 |  | Net Payment This Pay App | 76891.3 |  |  | 635.94
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date (Per Pay App #4) | Retainage To Date (Per Pay App #4) | Net Payment - This Pay App | Total Retainage (Cumulative)
1 | General Requirements | 124267.86 | 5955.65 | 297.78 | 45534.89 | 2276.74 | 5657.87
2 | Survey & Staking | 21650 | 2210 | 110.5 | 7758.75 | 387.94 | 2099.5
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 0 | 0 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 0 | 0 | 263850 | 13192.5 | 0
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 | 0 | 0
28 | Termite Control | 8084 | 0 | 0 | 0 | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 | 0 | 0
36 | General Conditions | 740250 | 59942.31 | 0 | 216803.5 | 0 | 59942.31
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1657.83 | 0 | 8411.22 | 0 | 1657.83
39 | Consturuction Fee | 438579.88 | 4553.16 | 227.66 | 40568.64 | 227.66 | 4325.5
40 | Sales Tax | 308277.78 | 3208.29 | 0 | 28515.69 | 0 | 3208.29
41 | [5 empty] | 0 | 0
42 | [5 empty] | 0 | 0
43 | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
47 | Sales Tax |  |  |  |  | 0 | 0
TOTALS |  | 7437427 | 77527.24 | 635.94 | 692847.52 | 19197.65 | 76891.3

## PayApp3
Pay Application #3 Summary (per AIA G702)
Gross This Pay App | 251277.37 |  | Net Payment This Pay App | 242871.03 |  |  | 8406.34
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date (Per Pay App #3) | Retainage To Date (Per Pay App #3) | Net Payment - This Pay App | Total Retainage (Cumulative)
1 | General Requirements | 124267.86 | 1429.77 | 78.34 | 39579.24 | 1978.96 | 1351.43
2 | Survey & Staking | 21650 | 5548.75 | 304.02 | 5548.75 | 277.44 | 5244.73
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 |  | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 |  | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 |  | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 |  | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 11332 | 620.89 | 11332 | 566.6 | 10711.11
8 | Roofing & Appendages | 467114 | 4671.14 | 255.93 | 4671.14 | 233.56 | 4415.21
9 | Joint Sealants | 18665 | 0 | 0 |  | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 |  | 0 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 |  | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 |  | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 |  | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 |  | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 |  | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 |  | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 |  | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 |  | 0 | 0
20 | Flagpole | 13475 | 0 | 0 |  | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 |  | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 |  | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 |  | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 |  | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 |  | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 130445 | 7147.16 | 263850 | 13192.5 | 123297.84
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 |  | 0 | 0
28 | Termite Control | 8084 | 0 | 0 |  | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 |  | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 |  | 0 | 0
31 | Contingency | 350000 | 0 | 0 |  | 0 | 0
32 |  | 0 | 0 | 0 |  | 0 | 0
33 |  | 0 | 0 | 0 |  | 0 | 0
34 |  | 0 | 0 | 0 |  | 0 | 0
35 |  | 0 | 0 | 0 |  | 0 | 0
36 | General Conditions | 740250 | 71177.88 | 0 | 156861.19 | 0 | 71177.88
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1647.83 | 0 | 6753.39 | 0 | 1647.83
39 | Consturuction Fee | 438579.88 | 14700 | 0 | 36015.48 | 0 | 14700
40 | Sales Tax | 308277.78 | 10325 | 0 | 25307.4 | 0 | 10325
41 | [5 empty] | 0 | 0
42 | [5 empty] | 0 | 0
43 | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
47 | Sales Tax |  |  |  |  | 0 | 0
TOTALS |  | 7437427 | 251277.37 | 8406.34 | 615500.28 | 18561.71 | 242871.03 | 18561.71

## PayApp2_Detail
Pay Application #2 Detail -
Item No. | Description of Work | Original Amount (Scheduled Value) | Earned to Date - This Pay App | % Complete to Date | Retainage $ | Retainage % | Net Payment This Pay App
1 | General Requirements | 124267.86 | 10593.57 | 8.525% | 1907.47 | 18.01% | 8686.1
2 | Survey & Staking | 21650 | 0 | 0 | 0 |  | 0
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 |  | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 |  | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 |  | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 |  | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 0 |  | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 0 |  | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 |  | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 0 |  | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 |  | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 |  | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 |  | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 |  | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 |  | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 |  | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 511.88 |  | -511.88
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 |  | 0
20 | Flagpole | 13475 | 0 | 0 | 0 |  | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 |  | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 |  | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 |  | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 |  | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 |  | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 47475 | 0.039367 | 6670.25 | 0.1405 | 40804.75
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 |  | 0
28 | Termite Control | 8084 | 0 | 0 | 0 |  | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 |  | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 |  | 0
31 | Contingency | 350000 | 0 | 0 | 0 |  | 0
32 |  | 0 | 0 |  | 0 |  | 0
33 |  | 0 | 0 |  | 0 |  | 0
34 |  | 0 | 0 |  | 0 |  | 0
35 |  | 0 | 0 |  | 0 |  | 0
36 |  | 0 | 0 |  | 0 |  | 0
37 |  | 0 | 0 |  | 0 |  | 0
38 |  | 0 | 0 |  | 0 |  | 0
39 |  | 0 | 0 |  | 0 |  | 0
40 |  | 0 | 0 |  | 0 |  | 0
41 |  | 0 | 0 |  | 0 |  | 0
42 |  | 0 | 0 |  | 0 |  | 0
43 | General Conditions | 740250 | 56942.31 | 0.076923 | 0 | 0 | 56942.31
44 | Bond | 55344 | 0 | 0 | 0 |  | 0
45 | Insurance | 63125.6 | 1637.83 | 0.025946 | 0 | 0 | 0
46 | Construction Fee (Overhead & Profit) | 438579.88 | 7587.81 | 0.017301 | 1065.77 | 0.14046 | 0
47 | Sales Tax | 308277.78 | 5333.31 | 0.0173 | 0 | 0 | 0
| TOTALS: |  | 129569.83 |  | 10155.37 |  | 126287.02
Check: Net Pay App #2 per AIA G702/G703 | 126287.02
Difference (Workbook Total - AIA Net) | 0

## PayApp1_Detail
Pay Application #1 Detail - Mirrors Contractor G703 (Option A)
Item No. | Description of Work | Original Amount (Scheduled Value) | Earned to Date - This Pay App | % Complete to Date | Retainage $ | Retainage % | Net Payment This Pay App
1 | General Requirements | 124267.86 | 27555.9 | 22.17% | 1377.8 | 5% | 26178.1
2 | Survey & Staking | 21650 | 0 | 0% | 0 |  | 0
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0% | 0 |  | 0
4 | Masonry & Precast | 512000 | 0 | 0% | 0 |  | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0% | 0 |  | 0
6 | Rough Carpentry | 212800 | 0 | 0% | 0 |  | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0% | 0 |  | 0
8 | Roofing & Appendages | 467114 | 0 | 0% | 0 |  | 0
9 | Joint Sealants | 18665 | 0 | 0% | 0 |  | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0% | 0 |  | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0% | 0 |  | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0% | 0 |  | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0% | 0 |  | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0% | 0 |  | 0
15 | Stucco | 106849.56 | 0 | 0% | 0 |  | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0% | 0 |  | 0
17 | Exterior & Interior Building Signage | 20475.37 | 10237.69 | 50% | 511.88 | 5% | 9725.81
18 | Toilet & Bath Accessories | 8845 | 0 | 0% | 0 |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0% | 0 |  | 0
20 | Flagpole | 13475 | 0 | 0% | 0 |  | 0
21 | Window Coverings | 4750 | 0 | 0% | 0 |  | 0
22 | Fire Sprinkler System | 36300 | 0 | 0% | 0 |  | 0
23 | Plumbing System | 240885 | 0 | 0% | 0 |  | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0% | 0 |  | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0% | 0 |  | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 85930 | 7.125% | 4296.5 | 5% | 81633.5
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0% | 0 |  | 0
28 | Termite Control | 8084 | 0 | 0% | 0 |  | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0% | 0 |  | 0
30 | Landscape & Irrigation | 49633 | 0 | 0% | 0 |  | 0
31 | Contingency | 350000 | 0 | 0% | 0 |  | 0
32 |  | 0 | 0 |  | 0 |  | 0
33 |  | 0 | 0 |  | 0 |  | 0
34 |  | 0 | 0 |  | 0 |  | 0
35 |  | 0 | 0 |  | 0 |  | 0
36 |  | 0 | 0 |  | 0 |  | 0
37 |  | 0 | 0 |  | 0 |  | 0
38 |  | 0 | 0 |  | 0 |  | 0
39 |  | 0 | 0 |  | 0 |  | 0
40 |  | 0 | 0 |  | 0 |  | 0
41 |  | 0 | 0 |  | 0 |  | 0
42 |  | 0 | 0 |  | 0 |  | 0
43 | General Conditions | 740250 | 28741 | 3.883% | 0 | 0% | 28741
44 | Bond | 55344 | 55344 | 100% | 0 | 0% | 55344
45 | Insurance | 63125.6 | 3287.73 | 5.208% | 0 | 0% | 3287.73
46 | Construction Fee (Overhead & Profit) | 438579.88 | 13727.67 | 3.13% | 686.38 | 5% | 13041.29
47 | Sales Tax | 308277.78 | 9649.09 | 3.13% | 0 | 0% | 9649.09
| TOTALS: |  | 234473.08 |  | 6872.56 |  | 227600.52

## GMP_Breakdown
GMP #1 Cost Summary (from Contractor Cost Summary Sheet)
A | Cost of Construction (Labor, Materials, Equipment) | 5538780.74
B | Contingency | 350000
C | Subtotal Direct Costs (A+B) | 5888780.74
D | General Conditions | 740250
E | Payment and Performance Bond | 55226
F | Insurance | 63125.6
G | Subtotal Indirect Costs (D+E+F) | 858601.6
H | Subtotal Direct and Indirect Costs (C+G) | 6747382.34
I | Construction Fee (Overhead & Profit) | 438579.88
J | Subtotal Direct and Indirect Costs (incl. Fee) | 7185962.22
K | Sales Tax | 308277.78
L/M | Total Amount (GMP #1) | 7494240