## USDA_Funding_Analysis
FUNDING ANALYSIS
Project Name: | Tubac Fire Station No. 1 |  | Pay Application #: | 9
Date: |  |  | Period To:
EXPENDITURES | Contractor | Budgeted | Obligated | Expended | Bal to Finish | Projected | Total | Curr Request | Notes
Construction – GMP | D.L. Norton General Contracting, Inc. | 7494240 | 7494240 | 3228591.71 | 4265648.29 |  | 7494240 | 686936.38 | Pay App #9 - Roof, canopy framing, shearwall framing, roofing, electrical rough in, plumbing rough in, fire sprinkler pipe instalation.
FUNDING SOURCES
Source | Total Budget | Prior Draw | This Draw | Balance Remaining | Notes
USDA Grant | 2000000 | 2000000 |  | 0 | Drawn first CDS grant.
Bond Funds | 4200000 | 1228591.71 | 683936.38 | 2287471.91 | Used after USDA funds are exhausted.
Capital Reserve | 1294240 | 0 | 0 | 1294240 | Drawn last; remaining balance stays in LPG account.
Contigency Funds | 350000 | 3500 |  | 346500 | Exploratory digging for water line

## Board_Chart
Pay App # | USDA | Bonds | Capital Reserve | Total Pay App
1 | 227600.52 | 0 | 0 | 227600.52
2 | 126287.02 | 0 | 0 | 126287.02
3 | 242871.03 | 0 | 0 | 242871.03
4 | 76891.3 | 0 | 0 | 76891.3
5 | 221948.64 | 0 | 0 | 221948.64
6 | 416100.82 |  |  | 416100.82
7 | 688300.67 | 185312.18 |  | 873612.85
8 |  | 1043279.53 |  | 1043279.53
9 |  | 683936.38 |  | 683936.38
Total | 2000000 | 1912528.09 |  | 3912528.09
Contingency Funds
Total | 350000
Used | 214012.81
Remaining | 135987.19

## USDA_Funding_Summary
USDA Funding Summary – Tubac Fire Station No. 1
Total Earned This Period | 1092343.95
Retainage | 49064.42
Net Pay Requested | 1043279.53
USDA Funds Applied This Pay App | 0
USDA Funds Drawn To Date | 2000000
USDA Grant Total | 2000000
USDA Remaining | 0
Bond Funds Used
This period | 683936.38
Total Bond Funds Applied | 1912528.09
Bond Funds remainig | 2287471.91
Bond funds avaialbe | 4200000

## Cumulative_Summary
Cumulative Net & Retainage Summary
Pay App # | Gross This Pay App | Retainage This Pay App | Net This Pay App | Cumulative Gross | Cumulative Retainage | Cumulative Net
1 | 234473.08 | 6872.56 | 227600.52 | 234473.08 | 6872.56 | 227600.52
2 | 129569.83 | 3282.81 | 126287.02 | 364042.91 | 10155.37 | 353887.54
3 | 251277.37 | 8406.34 | 242871.03 | 615320.28 | 18561.71 | 596758.57
4 | 77527.24 | 635.94 | 76891.3 | 692847.52 | 19197.65 | 673649.87
5 | 230220.45 | 8271.81 | 221948.64 | 923067.97 | 27469.46 | 895598.51
6 | 433977.73 | 17876.91 | 416100.82 | 1357045.7 | 45346.37 | 1311699.33
7 | 913468.42 | 39855.57 | 873612.85 | 2270514.12 | 85201.94 | 2185312.18
8 | 1092343.95 | 49064.42 | 1043279.53 | 3362858.07 | 134266.36 | 3228591.71
9 | 715071.25 | 31134.87 | 683936.38 | 4077929.32 | 165401.23 | 3912528.09

## SOV_Master
Division | Division Name | Item No. | Description | Unit | Qty | Unit Price | Bid Cost
1 | General Requirements | 1 | Safety/First Aid/ Eyewash Stn. | ls | 1 | 850 | 850
1 | General Requirements | 2 | Temporary Fire Protections | ls | 1 | 450 | 450
1 | General Requirements | 3 | Temporary Storage Container | ls | 1 | 2500 | 2500
1 | General Requirements | 4 | Temporary Building Protection | ls | 1 | 3000 | 3000
1 | General Requirements | 5 | Temporary Fence | ls | 1 | 6500 | 6500
1 | General Requirements | 6 | Temporary Job Trailer | ls | 1 | 30000 | 30000
1 | General Requirements | 7 | Temporary Power Job Trailer | ls | 1 | 13500 | 13500
1 | General Requirements | 8 | Job Trailer Drinking Water | ls | 1 | 1250 | 1250
1 | General Requirements | 9 | Temporary Toilets & Sanitation | ls | 1 | 7500 | 7500
1 | General Requirements | 10 | Temporary Handwash Station | ls | 1 | 1500 | 1500
1 | General Requirements | 11 | Progress & Final Cleaning | ls | 1 | 10500 | 10500
1 | General Requirements | 12 | Dumpster/Trash Disposal | ls | 1 | 24000 | 24000
1 | General Requirements | 13 | Street Sweeper | ls | 1 | 5000 | 5000
1 | General Requirements | 14 | Traffic Control | ls | 1 | 5800 | 5800
1 | General Requirements | 15 | Warranty | ls | 1 | 5000 | 5000
2 | Existing Conditions | 1 | Survey & Staking | ls | 1 | 21650 | 21650
3 | Concrete | 1 | Decorative Concrete Finishes | ls | 1 | 32006.85 | 32006.85
4 | Masonry & Precast Concrete | 1 | Masonry & Precast Concrete | ls | 1 | 512000 | 512000
5 | Metals | 1 | Structural Steel & Misc. Steel | ls | 1 | 136635 | 136635
6 | Wood, Plastics, and Composites | 1 | Rough Carpentry | ls | 1 | 257800 | 257800
6 | Wood, Plastics, and Composites | 2 | Architectural Wood & Countertop | ls | 1 | 113320 | 113320
7 | Thermal & Moisture Protection | 1 | Roofing & Appendages | ls | 1 | 427764 | 427764
7 | Thermal & Moisture Protection | 2 | Joint Sealants | ls | 1 | 18665 | 18665
8 | Openings | 1 | HM Frames, Doors & Hardware | ls | 1 | 92866 | 92866
8 | Openings | 2 | Aluminum Frames, Storefronts, Windows, Glazing | ls | 1 | 66596 | 66596
8 | Openings | 3 | Overhead Sectional & Coiling Doors | ls | 1 | 78610 | 78610
8 | Openings | 4 | Unit Skylights & Tubular Solatube | ls | 1 | 22691.12 | 22691.12
9 | Finishes | 1 | Framing, Insulation, Drywall, Paint, ACT, FRP | ls | 1 | 319743 | 319743
9 | Finishes | 2 | Stucco | ls | 1 | 106849.56 | 106849.56
9 | Finishes | 3 | Tile, Athletic Flooring, Rubber Base | ls | 1 | 29548 | 29548
10 | Specialties | 1 | Exterior & Interior Building Signage | ls | 1 | 22094 | 22094
10 | Specialties | 2 | Toilet & Bath Accessories | ls | 1 | 8845 | 8845
10 | Specialties | 3 | FEC (excludes fire extinguishers) & Corner Guards | ls | 1 | 4170 | 4170
10 | Specialties | 4 | Flagpoles | ls | 1 | 11781.31 | 11781.31
12 | Furnishings | 1 | Window Coverings | ls | 1 | 4750 | 4750
21 | Fire Suppression | 1 | Fire Sprinkler Systems | ls | 1 | 39000 | 39000
22 | Plumbing (Includes Mechanical) | 1 | Plumbing & Mechanical Systems | ls | 1 | 657153 | 657153
26 | Electrical (Includes Fire Alarm) | 1 | Electrical & Fire Alarm Systems | ls | 1 | 1058127 | 1058127
31/32 | Earthwork & Exterior Improvements | 1 | Demo, Fill, Grading, Utilities, Septic System, Building & Site Concrete and Asphalt | ls | 1 | 1205959.2 | 1205959.2
31/32 | Earthwork & Exterior Improvements | 2 | Asphalt Striping & Site Signage | ls | 1 | 3962.7 | 3962.7
31/32 | Earthwork & Exterior Improvements | 3 | Termite Control | ls | 1 | 8084 | 8084
31/32 | Earthwork & Exterior Improvements | 4 | Fence, Gates, Guardrail & Handrail | ls | 1 | 111127 | 111127
31/32 | Earthwork & Exterior Improvements | 5 | Landscape & Irrigation | ls | 1 | 49633 | 49633

## Pay_Apps
Pay Application Funding Tracker - Sequential Use of Funds (USDA → Bonds → Capital Reserve)
USDA Total | 2000000 | Bonds Total | 4200000 | Capital Reserve Total | 1294240 | GMP #1 Total | 7494240
|  |  |  | USDA - This Pay App | Running Total | Bonds - This Pay App |  | Capital Reserve - This Pay App |  | USDA Remaining | Bonds Remaining | Capital Reserve Remaining | Total Project Remaining
Pay App # | Date | Pay App Amount | Cummalative
1 | 2025-11-24 | 227600.52 | 227600.52 | 227600.52 | 227600.52 | 0 | 0 | 0 | 0 | 1772399.48 | 4200000 | 1294240 | 7266639.48
2 | 2025-11-28 | 126287.02 | 353887.54 | 126287.02 | 353887.54 | 0 | 0 | 0 | 0 | 1646112.46 | 4200000 | 1294240 | 7140352.46
3 | 2025-12-23 | 242871.03 | 596758.57 | 242871.03 | 596758.57 | 0 | 0 | 0 | 0 | 1403241.43 | 4200000 | 1294240 | 6897481.43
4 | 2026-01-28 | 76891.3 | 673649.87 | 76891.3 | 673649.87 | 0 | 0 | 0 | 0 | 1326350.13 | 4200000 | 1294240 | 6820590.13
5 | 2026-02-25 | 221948.64 | 895598.51 | 221948.64 | 895598.51 |  | 0 | 0 | 0 | 1104401.49 | 4200000 | 1294240 | 6598641.49
6 | 2026-03-26 | 416100.82 | 1311699.33 | 416100.82 | 1311699.33 | 0 | 0 | 0 | 0 | 688300.67 | 4200000 | 1294240 | 6182540.67
7 | 2026-04-29 | 873612.85 | 2185312.18 | 688300.67 | 2000000 | 185312.18 | 185312.18 | 0 | 0 | 0 | 4014687.82 | 1294240 | 5308927.82
8 | 2026-05-27 | 1043279.53 | 3228591.71 | 0 | 2000000 | 1043279.53 | 1228591.71 | 0 | 0 | 0 | 2971408.29 | 1294240 | 4265648.29
9 | 2026-06-30 | 683936.38 | 3912528.09 | 0 | 2000000 | 683936.38 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91
|  |  | 3912528.09 | 0 | 2000000 | 0 | 1912528.09 | 0 | 0 | 0 | 2287471.91 | 1294240 | 3581711.91

## PayApp9
Pay Application #9 Summary (per AIA G702)
Item No | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date | Retainage To Date (Per Pay App #9) | Net This pay app
1 | General Requirements | 124267.86 | 3355.8 | 167.79 | 69560.11 | 3478.01 | 3188.01
2 | Survey & Staking | 21650 | 2378.75 | 118.94 | 20650 | 1032.5 | 2259.81
3 | Decorative Concrete Finishes | 39955.86 |  | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 12477.5 | 623.88 | 451900 | 22595 | 11853.62
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 114414 | 5720.7 | 0
6 | Rough Carpentry | 212800 | 16100 | 805 | 181047 | 9052.35 | 15295
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 62326 | 3116.3 | 0
8 | Roofing & Appendages | 467114 | 6973.34 | 348.66 | 306926.88 | 15346.34 | 6624.68
9 | Joint Sealants | 18665 | 5599.5 | 279.98 | 5599.5 | 279.98 | 5319.52
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 59382 | 2969.1 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 20680 | 1034 | 41925 | 2096.25 | 19646
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 11345.5 | 567.28 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 65497 | 3274.85 | 173741 | 8687.05 | 62222.15
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 |  | 0
20 | Flagpole | 13475 | 0 | 0 | 0 |  | 0
21 | Window Coverings | 4750 |  | 0 | 0 |  | 0
22 | Fire Sprinkler System | 36300 | 25410 | 1270.5 | 29040 | 1452 | 24139.5
23 | Plumbing System | 240885 | 58127 | 2906.35 | 183250.37 | 9162.52 | 55220.65
24 | Mechanical / HVAC System | 396268 | 113368.32 | 5668.41 | 233023.05 | 11651.15 | 107699.91
25 | Electrical & Fire Alarm Systems | 1063127 | 53156.35 | 2657.81 | 318938.1 | 15946.9 | 50498.54
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 135633 | 6781.65 | 716686.5 | 35834.33 | 128851.35
27 | Asphalt Striping & Site Signage | 3962.7 |  | 0 | 0 | 0 | 0
28 | Termite Control | 8084 |  | 0 | 5525 | 276.25 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 |  | 0 | 8000 | 400 | 0
30 | Landscape & Irrigation | 49633 |  | 0 | 0 |  | 0
31 | Contingency | 350000 | 62100.31 | 3293.77 | 65875.31 | 3293.77 | 58806.54
32 |  | 0 |  | 0 | 0 |  | 0
33 |  | 0 |  | 0 | 0 |  | 0
34 |  | 0 |  | -188.75 |  |  | 188.75
35 |  | 0 |  | 0 | 0 |  | 0
36 | General Conditions | 740250 | 56942.31 | 0 | 512480.77 |  | 56942.31
37 | Bond | 55344 | 0 | 0 | 55344 |  | 0
38 | Insurance | 6312.6 | 6021.85 | 0 | 34346.31 |  | 6021.85
39 | Consturuction Fee | 438579.88 | 41840.52 | 2092.03 | 238631.31 | 11931.57 | 39748.49
40 | Sales Tax | 308277.78 | 29409.7 | 0 | 167733.94 |  | 29409.7
| Totales | 7437427 | 715071.25 | 31134.87 | 4077929.34 | 165401.23 | 683936.38
Note on D3: Ben Guerrero: Line E
Note on F3: Ben Guerrero: Column G
Note on G3: Ben Guerrero: Column I

## PayApp8
Pay Application #8 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | Retainage - This Pay App | Retainage To Date (Per Pay App #8) | Completed To Date | Net This pay app
1 | General Requirements | 124267.86 | 194.05 | 3310.22 | 66204.31 | 3880.9
2 | Survey & Staking | 21650 | 71.75 | 913.56 | 18271.25 | 1435
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 2966.12 | 21971.12 | 439422.5 | 59322.5
5 | Structural Steel & Misc. Steel | 131460 | 1170 | 5720.7 | 114414 | 23400
6 | Rough Carpentry | 212800 | 2567.65 | 8247.35 | 164947 | 51353
7 | Architectural Wood & Countertops | 113320 | 2549.7 | 3116.3 | 62326 | 50994
8 | Roofing & Appendages | 467114 | 14764.12 | 14997.68 | 299953.52 | 295282.38
9 | Joint Sealants | 18665 | 0 | 0 | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 2969.1 | 59382 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 1062.25 | 1062.25 | 21245 | 21245
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 567.28 | 11345.5 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 2157.55 | 5412.2 | 108244 | 43151
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 511.88 | 10237.69 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 181.5 | 3630 | 0
23 | Plumbing System | 240885 | 1105.15 | 6256.17 | 125123.37 | 22102.98
24 | Mechanical / HVAC System | 396268 | 5141.84 | 5982.74 | 119654.73 | 102836.73
25 | Electrical & Fire Alarm Systems | 1063127 | 9036.58 | 13289.09 | 265781.75 | 180731.59
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 2217.6 | 29052.68 | 581053.5 | 44352
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 | 0
28 | Termite Control | 8084 | 276.25 | 276.25 | 5525 | 5525
29 | Fence, Gates, Guardrail & Handrail | 111127 | 400 | 400 | 8000 | 8000
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 3775 | 0
32 |  | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 188.75 | 188.75 |  | 3775
35 |  | 0 | 0 | 0 | 0 | 0
36 | General Conditions | 740250 | 0 | 0 | 455538.46 | 56942.31
37 | Bond | 55344 | 0 | 0 | 55344 | 0
38 | Insurance | 6312.6 | 0 | 0 | 28324.46 | 9197.4
39 | Consturuction Fee | 438579.88 | 3195.06 | 9839.54 | 196790.79 | 63901.09
40 | Sales Tax | 308277.78 | 0 | 0 | 138324.24 | 44916.07
| Totales | 7437427 | 49064.42 | 134266.36 | 3362858.07 | 1092343.95

## PayApp7
Pay Application #7 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date | Retainage To Date (Per Pay App #7) | Net This pay app
1 | General Requirements | 124267.86 | 3031.32 | 151.57 | 62323.41 | 3116.17 | 2879.75
2 | Survey & Staking | 21650 | 4047.5 | 202.37 | 16836.25 | 841.81 | 3845.13
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 |  | 0 | 0
4 | Masonry & Precast | 512000 | 370000 | 18500 | 380100 | 19005 | 351500
5 | Structural Steel & Misc. Steel | 131460 | 67899 | 3394.95 | 91014 | 4550.7 | 64504.05
6 | Rough Carpentry | 212800 | 113594 | 5679.7 | 113594 | 5679.7 | 107914.3
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 |  | 0 |  | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 59382 | 2969.1 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 |  | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 |  | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 |  | 0 | 11345.5 | 567.28 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 12369.4 | 618.47 | 65093 | 3254.65 | 11750.93
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 |  | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 |  |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 |  |  | 0
20 | Flagpole | 13475 | 0 | 0 | 0 |  | 0
21 | Window Coverings | 4750 | 0 | 0 |  | 0 | 0
22 | Fire Sprinkler System | 36300 | 3630 | 181.5 | 3630 | 181.5 | 3448.5
23 | Plumbing System | 240885 | 103020.39 | 5151.02 | 103020.39 | 5151.02 | 97869.37
24 | Mechanical / HVAC System | 396268 | 16818 | 840.9 | 16818 | 840.9 | 15977.1
25 | Electrical & Fire Alarm Systems | 1063127 | 31893.81 | 1594.69 | 85050.16 | 4252.51 | 30299.12
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 17345 | 867.26 | 536701.5 | 26835.08 | 16477.74
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 |  | 0 | 0
28 | Termite Control | 8084 | 0 | 0 |  | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 |  | 0
36 | General Conditions | 740250 | 71177.88 | 0 | 398596.15 | 0 | 71177.88
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 7600.18 | 0 | 19127.06 | 0 | 7600.18
39 | Consturuction Fee | 438579.88 | 53462.88 | 2673.14 | 132889.7 | 6644.48 | 50789.74
40 | Sales Tax | 308277.78 | 37579.06 | 0 | 93408.17 | 0 | 37579.06
| Totales | 7437427 | 913468.42 | 39855.57 | 2270514.12 | 85201.94 | 873612.85

## PayApp6
Pay Application #6 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date | Retainage To Date (Per Pay App #6) | Net This pay app
1 | General Requirements | 124267.86 | 8269.57 | 413.47 | 59292.09 | 2964.6 | 7856.1
2 | Survey & Staking | 21650 | 3455 | 172.75 | 12788.75 | 639.44 | 3282.25
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 |  | 0 | 0
4 | Masonry & Precast | 512000 | 10100 | 505 | 10100 | 505 | 9595
5 | Structural Steel & Misc. Steel | 131460 | 23115 | 1155.75 | 23115 | 1155.75 | 21959.25
6 | Rough Carpentry | 212800 | 0 | 0 | 0 | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 |  | 0 |  | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 59382 | 2969.1 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 |  | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 |  | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 11345.5 | 567.28 | 11345.5 | 567.28 | 10778.22
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 52723.6 | 2636.18 | 52723.6 | 2636.18 | 50087.42
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 |  | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 |  | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 |  | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 |  | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 |  | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 |  | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 |  | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 53156.35 | 2657.82 | 53156.35 | 2657.82 | 50498.53
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 169979.5 | 8498.97 | 519356.5 | 25967.82 | 161480.53
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 |  | 0 | 0
28 | Termite Control | 8084 | 0 | 0 |  | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 |  | 0
36 | General Conditions | 740250 | 56942.31 | 0 | 327418.27 | 0 | 56942.31
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1647.83 | 0 | 11526.88 | 0 | 1647.83
39 | Consturuction Fee | 438579.88 | 25393.78 | 1269.69 | 79426.82 | 3971.34 | 24124.09
40 | Sales Tax | 308277.78 | 17849.29 | 0 | 55829.11 | 0 | 17849.29
| Totales | 7437427 | 433977.73 | 17876.91 | 1357045.7 | 45346.37 | 416100.82

## PayApp5
Pay Application #5 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date | Retainage To Date (Per Pay App #4) | Net This pay app
1 | General Requirements | 124267.86 | 5487.63 | 205.62 | 51022.52 | 2551.13 | 5282.01
2 | Survey & Staking | 21650 | 1575 | 59.02 | 9333.75 | 466.69 | 1515.98
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 59382 | 2225.06 | 59382 | 2969.1 | 57156.94
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 85527 | 3204.72 | 349377 | 17468.85 | 82322.28
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 | 0 | 0
28 | Termite Control | 8084 | 0 | 0 | 0 | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 | 0 | 0
36 | General Conditions | 740250 | 53672.46 | 2011.12 | 270475.96 | 0 | 51661.34
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1647.83 | 61.75 | 9879.05 | 0 | 1586.08
39 | Consturuction Fee | 438579.88 | 13464.4 | 504.52 | 54033.04 | 2701.65 | 12959.88
40 | Sales Tax | 308277.78 | 9464.13 | 0 | 37979.82 | 0 | 9464.13
| Totales | 7437427 | 230220.45 | 8271.81 | 923067.97 | 27469.46 | 221948.64

## PayApp4
Pay Application #4 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date (Per Pay App #4) | Retainage To Date (Per Pay App #4) | Net Payment - This Pay App | Total Retainage (Cumulative)
1 | General Requirements | 124267.86 | 5955.65 | 297.78 | 45534.89 | 2276.74 | 5657.87
2 | Survey & Staking | 21650 | 2210 | 110.5 | 7758.75 | 387.94 | 2099.5
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 11332 | 566.6 | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 4671.14 | 233.56 | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 0 | 0 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 | 0 | 0
20 | Flagpole | 13475 | 0 | 0 | 0 | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 0 | 0 | 263850 | 13192.5 | 0
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 | 0 | 0
28 | Termite Control | 8084 | 0 | 0 | 0 | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 | 0 | 0
31 | Contingency | 350000 | 0 | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 | 0 | 0
36 | General Conditions | 740250 | 59942.31 | 0 | 216803.5 | 0 | 59942.31
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1657.83 | 0 | 8411.22 | 0 | 1657.83
39 | Consturuction Fee | 438579.88 | 4553.16 | 227.66 | 40568.64 | 227.66 | 4325.5
40 | Sales Tax | 308277.78 | 3208.29 | 0 | 28515.69 | 0 | 3208.29
41 | [5 empty] | 0 | 0
42 | [5 empty] | 0 | 0
43 | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
47 | Sales Tax |  |  |  |  | 0 | 0
TOTALS |  | 7437427 | 77527.24 | 635.94 | 692847.52 | 19197.65 | 76891.3

## PayApp3
Pay Application #3 Summary (per AIA G702)
Item No. | Description | Schedule of Values (SOV) | This Pay App | Retainage - This Pay App | Completed To Date (Per Pay App #3) | Retainage To Date (Per Pay App #3) | Net Payment - This Pay App | Total Retainage (Cumulative)
1 | General Requirements | 124267.86 | 1429.77 | 78.34 | 39579.24 | 1978.96 | 1351.43
2 | Survey & Staking | 21650 | 5548.75 | 304.02 | 5548.75 | 277.44 | 5244.73
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 |  | 0 | 0
4 | Masonry & Precast | 512000 | 0 | 0 |  | 0 | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 |  | 0 | 0
6 | Rough Carpentry | 212800 | 0 | 0 |  | 0 | 0
7 | Architectural Wood & Countertops | 113320 | 11332 | 620.89 | 11332 | 566.6 | 10711.11
8 | Roofing & Appendages | 467114 | 4671.14 | 255.93 | 4671.14 | 233.56 | 4415.21
9 | Joint Sealants | 18665 | 0 | 0 |  | 0 | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 |  | 0 | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 |  | 0 | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 |  | 0 | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 |  | 0 | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 |  | 0 | 0
15 | Stucco | 106849.56 | 0 | 0 |  | 0 | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 |  | 0 | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 10237.69 | 511.88 | 0
18 | Toilet & Bath Accessories | 8845 | 0 | 0 |  | 0 | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 |  | 0 | 0
20 | Flagpole | 13475 | 0 | 0 |  | 0 | 0
21 | Window Coverings | 4750 | 0 | 0 |  | 0 | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 |  | 0 | 0
23 | Plumbing System | 240885 | 0 | 0 |  | 0 | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 |  | 0 | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 |  | 0 | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 130445 | 7147.16 | 263850 | 13192.5 | 123297.84
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 |  | 0 | 0
28 | Termite Control | 8084 | 0 | 0 |  | 0 | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 |  | 0 | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 |  | 0 | 0
31 | Contingency | 350000 | 0 | 0 |  | 0 | 0
32 |  | 0 | 0 | 0 |  | 0 | 0
33 |  | 0 | 0 | 0 |  | 0 | 0
34 |  | 0 | 0 | 0 |  | 0 | 0
35 |  | 0 | 0 | 0 |  | 0 | 0
36 | General Conditions | 740250 | 71177.88 | 0 | 156861.19 | 0 | 71177.88
37 | Bond | 55344 | 0 | 0 | 55344 | 0 | 0
38 | Insurance | 6312.6 | 1647.83 | 0 | 6753.39 | 0 | 1647.83
39 | Consturuction Fee | 438579.88 | 14700 | 0 | 36015.48 | 0 | 14700
40 | Sales Tax | 308277.78 | 10325 | 0 | 25307.4 | 0 | 10325
41 | [5 empty] | 0 | 0
42 | [5 empty] | 0 | 0
43 | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
47 | Sales Tax |  |  |  |  | 0 | 0
TOTALS |  | 7437427 | 251277.37 | 8406.34 | 615500.28 | 18561.71 | 242871.03 | 18561.71

## PayApp2_Detail
Pay Application #2
Item No. | Description of Work | Original Amount (Scheduled Value) | Earned to Date - This Pay App | % Complete to Date | Retainage $ | Retainage % | Net Payment This Pay App
1 | General Requirements | 124267.86 | 10593.57 | 8.525% | 1907.47 | 18.01% | 8686.1
2 | Survey & Staking | 21650 | 0 | 0 | 0 |  | 0
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0 | 0 |  | 0
4 | Masonry & Precast | 512000 | 0 | 0 | 0 |  | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0 | 0 |  | 0
6 | Rough Carpentry | 212800 | 0 | 0 | 0 |  | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0 | 0 |  | 0
8 | Roofing & Appendages | 467114 | 0 | 0 | 0 |  | 0
9 | Joint Sealants | 18665 | 0 | 0 | 0 |  | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0 | 0 |  | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0 | 0 |  | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0 | 0 |  | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0 | 0 |  | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0 | 0 |  | 0
15 | Stucco | 106849.56 | 0 | 0 | 0 |  | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0 | 0 |  | 0
17 | Exterior & Interior Building Signage | 20475.37 | 0 | 0 | 511.88 |  | -511.88
18 | Toilet & Bath Accessories | 8845 | 0 | 0 | 0 |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0 | 0 |  | 0
20 | Flagpole | 13475 | 0 | 0 | 0 |  | 0
21 | Window Coverings | 4750 | 0 | 0 | 0 |  | 0
22 | Fire Sprinkler System | 36300 | 0 | 0 | 0 |  | 0
23 | Plumbing System | 240885 | 0 | 0 | 0 |  | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0 | 0 |  | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0 | 0 |  | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 47475 | 0.039367 | 6670.25 | 0.1405 | 40804.75
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0 | 0 |  | 0
28 | Termite Control | 8084 | 0 | 0 | 0 |  | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0 | 0 |  | 0
30 | Landscape & Irrigation | 49633 | 0 | 0 | 0 |  | 0
31 | Contingency | 350000 | 0 | 0 | 0 |  | 0
32 |  | 0 | 0 |  | 0 |  | 0
33 |  | 0 | 0 |  | 0 |  | 0
34 |  | 0 | 0 |  | 0 |  | 0
35 |  | 0 | 0 |  | 0 |  | 0
36 |  | 0 | 0 |  | 0 |  | 0
37 |  | 0 | 0 |  | 0 |  | 0
38 |  | 0 | 0 |  | 0 |  | 0
39 |  | 0 | 0 |  | 0 |  | 0
40 |  | 0 | 0 |  | 0 |  | 0
41 |  | 0 | 0 |  | 0 |  | 0
42 |  | 0 | 0 |  | 0 |  | 0
43 | General Conditions | 740250 | 56942.31 | 0.076923 | 0 | 0 | 56942.31
44 | Bond | 55344 | 0 | 0 | 0 |  | 0
45 | Insurance | 63125.6 | 1637.83 | 0.025946 | 0 | 0 | 0
46 | Construction Fee (Overhead & Profit) | 438579.88 | 7587.81 | 0.017301 | 1065.77 | 0.14046 | 0
47 | Sales Tax | 308277.78 | 5333.31 | 0.0173 | 0 | 0 | 0
| TOTALS: |  | 129569.83 |  | 10155.37 |  | 126287.02
Check: Net Pay App #2 per AIA G702/G703 | 126287.02
Difference (Workbook Total - AIA Net) | 0

## PayApp1_Detail
Pay Application #1
Item No. | Description of Work | Original Amount (Scheduled Value) | Earned to Date - This Pay App | % Complete to Date | Retainage $ | Retainage % | Net Payment This Pay App
1 | General Requirements | 124267.86 | 27555.9 | 22.17% | 1377.8 | 5% | 26178.1
2 | Survey & Staking | 21650 | 0 | 0% | 0 |  | 0
3 | Decorative Concrete Finishes | 39955.86 | 0 | 0% | 0 |  | 0
4 | Masonry & Precast | 512000 | 0 | 0% | 0 |  | 0
5 | Structural Steel & Misc. Steel | 131460 | 0 | 0% | 0 |  | 0
6 | Rough Carpentry | 212800 | 0 | 0% | 0 |  | 0
7 | Architectural Wood & Countertops | 113320 | 0 | 0% | 0 |  | 0
8 | Roofing & Appendages | 467114 | 0 | 0% | 0 |  | 0
9 | Joint Sealants | 18665 | 0 | 0% | 0 |  | 0
10 | HM Frames, Doors & Hardware | 92866 | 0 | 0% | 0 |  | 0
11 | Aluminum Frames, Storefronts, Windows, Glass & Glazing | 67490 | 0 | 0% | 0 |  | 0
12 | Overhead Coiling & Sectional Doors | 78610 | 0 | 0% | 0 |  | 0
13 | Unit Skylights & Tubular Solatube | 22691.12 | 0 | 0% | 0 |  | 0
14 | Framing, Insulation, Drywall, Paint, ACT & FRP | 323005 | 0 | 0% | 0 |  | 0
15 | Stucco | 106849.56 | 0 | 0% | 0 |  | 0
16 | Tile, Athletic Flooring & Rubber Base | 38857.07 | 0 | 0% | 0 |  | 0
17 | Exterior & Interior Building Signage | 20475.37 | 10237.69 | 50% | 511.88 | 5% | 9725.81
18 | Toilet & Bath Accessories | 8845 | 0 | 0% | 0 |  | 0
19 | FEC & Corner Guards (excl. fire extinguishers) | 4170 | 0 | 0% | 0 |  | 0
20 | Flagpole | 13475 | 0 | 0% | 0 |  | 0
21 | Window Coverings | 4750 | 0 | 0% | 0 |  | 0
22 | Fire Sprinkler System | 36300 | 0 | 0% | 0 |  | 0
23 | Plumbing System | 240885 | 0 | 0% | 0 |  | 0
24 | Mechanical / HVAC System | 396268 | 0 | 0% | 0 |  | 0
25 | Electrical & Fire Alarm Systems | 1063127 | 0 | 0% | 0 |  | 0
26 | Demo, Import Fill, Grading, Septic System, Utilities, Building & Site Concrete and Asphalt | 1205959.2 | 85930 | 7.125% | 4296.5 | 5% | 81633.5
27 | Asphalt Striping & Site Signage | 3962.7 | 0 | 0% | 0 |  | 0
28 | Termite Control | 8084 | 0 | 0% | 0 |  | 0
29 | Fence, Gates, Guardrail & Handrail | 111127 | 0 | 0% | 0 |  | 0
30 | Landscape & Irrigation | 49633 | 0 | 0% | 0 |  | 0
31 | Contingency | 350000 | 0 | 0% | 0 |  | 0
32 |  | 0 | 0 |  | 0 |  | 0
33 |  | 0 | 0 |  | 0 |  | 0
34 |  | 0 | 0 |  | 0 |  | 0
35 |  | 0 | 0 |  | 0 |  | 0
36 |  | 0 | 0 |  | 0 |  | 0
37 |  | 0 | 0 |  | 0 |  | 0
38 |  | 0 | 0 |  | 0 |  | 0
39 |  | 0 | 0 |  | 0 |  | 0
40 |  | 0 | 0 |  | 0 |  | 0
41 |  | 0 | 0 |  | 0 |  | 0
42 |  | 0 | 0 |  | 0 |  | 0
43 | General Conditions | 740250 | 28741 | 3.883% | 0 | 0% | 28741
44 | Bond | 55344 | 55344 | 100% | 0 | 0% | 55344
45 | Insurance | 63125.6 | 3287.73 | 5.208% | 0 | 0% | 3287.73
46 | Construction Fee (Overhead & Profit) | 438579.88 | 13727.67 | 3.13% | 686.38 | 5% | 13041.29
47 | Sales Tax | 308277.78 | 9649.09 | 3.13% | 0 | 0% | 9649.09
| TOTALS: |  | 234473.08 |  | 6872.56 |  | 227600.52

## GMP_Breakdown
GMP #1 Cost Summary (from Contractor Cost Summary Sheet)
A | Cost of Construction (Labor, Materials, Equipment) | 5538780.74
B | Contingency | 350000
C | Subtotal Direct Costs (A+B) | 5888780.74
D | General Conditions | 740250
E | Payment and Performance Bond | 55226
F | Insurance | 63125.6
G | Subtotal Indirect Costs (D+E+F) | 858601.6
H | Subtotal Direct and Indirect Costs (C+G) | 6747382.34
I | Construction Fee (Overhead & Profit) | 438579.88
J | Subtotal Direct and Indirect Costs (incl. Fee) | 7185962.22
K | Sales Tax | 308277.78
L/M | Total Amount (GMP #1) | 7494240